## Sheet1
Related User Story | Task Description | Team Member | Initial Estimate (hours) | Amount Remaining After…
|  |  |  | Week 1 | Week 2
Plan Meals for the next week | Use case scenario for planning meals | Jordan | 1 | 1
| wireframe for palnning view (mobile) | Jordan | 2 | 1
| wireframe for palnning view (web) | Ben | 2 | 2 | 0
| wireframe for daily plan detail(mobile) | Jordan | 1 | 1
| wireframe for daily plan detail (web) | Ben | 1 | 0 | 0
| Implement wireframe design (web) | Ben | 3 | 2 | 0
| Implement wireframe design (mobile) | Jordan | 2 | 0 | 2
| database implementation of date tracking | Brianna | 2 | 0 | 0
| database implementation of meal plan storing | Brianna | 2 | 2 | 0
| database implementation of day and meal slots | Brianna | 2 | 0 | 0
| Api implementation of meal planning | Brianna | 3 | 3 | 0
| Api implementation of meals | Brianna | 3 | 3 | 0
| Mobile implementation of meal plan class | Jordan | 1 | 1 | 0
| Web implementation of meal plan retreival | Ben | 1 | 1 | 0
| Mobile implementation of calendar/planner | Jordan | 2 | 0 | 1
| web implementation of calendar/planner | Ben | 3 | 2 | 0
| Mobile implementation of add recipe to plan button | Jordan | 2 | 0 | 2
| Web implementation of adding a recipe to meal plan day/slot | Ben | 2 | 2 | 0
| Allow for meal plan editing mobile | Jordan | 1 |  | 1
| Allow for meal plan editing web | Ben | 3 | 3 | 0
| allow for access of next planned meals to be shown on main screen (web) | Ben | 2 | 2 | 0
| allow for access of next planned meals to be shown on main screen (mobile) | Jordan | 2 | 0 | 0
| backend meal plan editing end points | Brianna | 4 | 4 | 0
Generate a Shopping List for planned Meals | backend list comparison between pantry and meal plan ingredients | Brianna | 3 | 3 | 3
| Wireframe for grocery list (Mobile) | Jordan | 1 | 1
| Wireframe for grocery list (web) | Ben | 1 | 0 | 0
| use case scenario for generate shopping list | Jordan | 1 | 0.5
| Implement wire frame (mobile) | Jordan | 1 | 0 | 0
| Implement wire frame (web) | Ben | 3 | 3
| Viewmodel for grocery list view (Mobile) | Jordan | 2 | 0 | 0
| Backend ensure conversion of units works | Brianna | 1 | 1 | 1
Filter Recipes by type | Filter by multiple diets (web) | Ben | 1 | 1 | 0
| Filter by multiple diets (Mobile) | Jordan | 1 | 1
| Filter by cuisine (mobile) | Jordan | 1 |  | 1
Fixes | Email format check (mobile) | Jordan | 0.5 | 0.5
| Change search by name label | Jordan | 0.1 | 0.1
| Change registration back to single screen (mobile) | Jordan | 0.5 | 0.5
| New user pantry crash due to null list (mobile) | Jordan | 0.5 | 0.5
| ERD | Brianna | 1 | 0 | 0
| Estimate Totals |  | 60 | 38.5 | 10