## Sheet1
Related User Story | Task Description | Team Member | Initial Estimate (hours) | Amount Remaining After…
|  |  |  | Week 1 | Week 2
Manage available Ingredients | Fix bug that prevented addition of ingredient to empty pantry | Jordan | 1 | 1
| Add selection of measurement unit to add ingredient (Desktop) | Jordan | 1 | 1
| Add measurement unit to backend (there is a convert amounts endpoint that looks like we can convert ingredients to specific measurements.) | Brianna | 4 | 2 | 0
| Add selection of measurement unit to add ingredient (Web) | Ben | 2 | 2 | 0
| make pantry page a tiled display with add feature next to header (Web) | Jordan | 1 | 1
| Fix adding ingredient with long name causes crash | Brianna | 1 | 0 | 0
| Send http responses from api instead of letting it crash | Brianna | 2 | 0 | 0
| Add standard ingredients to database | Brianna | 2 | 0 | 0
Filter Recipes by type
| Setup back end call to spoonacular based on type (https://spoonacular.com/food-api/docs#Meal-Types) | Brianna | 2 | 2 | 0
| Implement combobox to choosed type of recipe to browse. (Desktop) | Jordan | 1 |  | 1
| Implement a way for user to choose type of recipe to browse (web) | Ben | 3 | 3 | 0
| Write filter recipes by type use case scenario | Jordan | 1 |  | 1
| ensure filter is considered when calling backend api from web | Ben | 2 | 2 | 0
| ensure filter is considered when calling backend api from Desktop | jordan | 1 |  | 1
Browsing Recipes
| Paginate results and present them in a user friendly way (Desktop) | Jordan | 2 |  | 2
| Create BrowseRecipe wireframe (Desktop) | Jordan | 1 | 0.5 | 0.5
| Write Browse Recipes use case scenario | Jordan | 0.5 | 0.5 | 0.5
| Create BrowseRecipe wireframe (web) | Ben | 1 | 1 | 0
| Implement wireframe design (Desktop) | Jordan | 1 |  | 2
| Implement wireframe design (Web) | Ben | 3 | 3 | 0
| Create method for desktop to browse recipes by calling back end | Brianna | 3 | 3 | 0
| Web call to backend to browse recipes | Ben | 1 | 1 | 0
| Include image with recipe info retrieved from api | Brianna | 0.5 | 0.5 | 0
| Update class diagram | Brianna | 3 | 3 | 0
| Update ERD | Brianna | 0.5 | 0.5 | 0
| Search recipes by name (Desktop) | Jordan | 1 |  | 0.5
| Search recipes by name (Web) | Ben | 1 | 1 | 0
Find Recipes using available Ingredients | Adjust backend to try and have more matching results returned. | Brianna | 3 | 1 | 0
| add custom checks for format expectations login/register (web) | Ben | 2 | 2 | 0
| add custom checks for format expectations login/register (desktop) | Jordan | 1 | 1
| Have user enter password twice registering (Web) | Ben | 0.5 | 0.5 | 0
| Text wrap on recipe detail steps (Desktop) | Jordan | 1 | 2
| hamburger menu does not display properly on recipe details page | Jordan | 0.5 | 0.5
| Have user enter password twice registering (Desktop) | Jordan | 0.5 | 0.5
| Estimate Totals |  | 51 | 35.5 | 8.5