## Sheet1
Related User Story | Task Description | Team Member | Initial Estimate (hours) | Amount Remaining After…
|  |  |  | Week 1 | Week 2
Manage available Ingredients | Design and test basic Pantry class, (constructor, getters, setters) | Jordan | 1 | 1 | 0
| Implement serialization of user pantry between data base and apps. | Jordan | 3 | 0 | 0
| Implement methods for user class to interact with pantry (add, edit, etc) desk | Jordan | 2 | 0 | 2
| Implement methods for user class to interact with pantry (add, edit, etc) web | Ben | 2 | 2 | 0
| Implement wire framed ui for user to interact with pantry. Desk | Jordan | 1 | 2 | 2
| Implement wire framed ui for user to interact with pantry. Web | Ben | 2 | 2 | 0
| Implement view model details to show updated pantry/fetched pantry desktop | Jordan | 2 | 0 | 3
| Implement view model details to show updated pantry/fetched pantry web app | Ben | 2 | 2
| Standardize quantity measurement for pantry ingredients | Brianna | 2 | 2
| design wire frame pantry screen desktop | Jordan | 1 | 1 | 0
| design wire frame pantry screen Web | Ben | 1 | 0 | 0
Find Recipes using available Ingredients | Establish connection with recipe api | Brianna | 2 | 0
| Query api with pantry ingredients | Brianna | 1 | 0
| Parse recipes to ensure theyre qualified as results | Brianna | 2 | 1
| Wire frame design for recipe results desktop | Jordan | 1 | 1 | 0
| Wire frame design for recipe results web | Ben | 1 | 0 | 0
| implement ui from wireframe desk | Jordan | 1 | 6 | 2
| implement ui from wireframe web | Ben | 3 | 3 | 0
| implement view model for results desk | Jordan | 1 | 2 | 2
| implement view model for results web | Ben | 2 | 2 | 0
| implement recipe model class desk | Jordan | 2 | 0 | 1
| implement recipe model class web | Brianna | 2
Catching up tasks | Connect web app to db | Ben | 2 | 0 | 0
| Test web app classes and produce coverage report | Ben | 4 | 0 | 0
| Finish login web app process. | Ben | 2 | 0 | 0
| Implement hashing for password submission between apps and db | Brianna | 1
| Design wire frame desktop login/main page | Brianna | 1 | 0
| Design wire frame web app login/main page | Brianna | 1 | 0
| Use Case Scenario's | Jordan | 1 | 2 | 1
| ERD | Brianna | 3 | 0
| Main page wire frame | Jordan | 1 | 1 | 0
| Implement registration in backend | Brianna | 2 | 2
| Estimate Totals |  | 55 | 32 | 13