## Sheet1
Related User Story | Task Description | Team Member | Initial Estimate (hours) | Amount Remaining After…
|  |  |  | Week 1 | Week 2
Generate a Shopping List for planned Meals | backend list comparison between pantry and meal plan ingredients | Brianna | 5 | 3 | 0
| Implement wire frame (mobile) | Jordan | 3 | 2 | 0
| Implement wire frame (web) | Ben | 3 | 2 | 0
| Viewmodel for grocery list view (Mobile) | Jordan | 3 | 3 | 2
| Backend ensure conversion of units works | Brianna | 5 | 3 | 0
| Stylize message box (Mobile) | Jordan | 2 | 1 | 0
| Add/remove/deduct ingredients for grocery list (Mobile) | Jordan | 1 |  | 1
| Add/remove/deduct ingredients for grocery list backend | Brianna | 3 | 0 | 0
| Add/remove/deduct ingredients for grocery list (web) | Ben | 4 | 1 | 0
Plan Meals for the next week | Allow meals to be added from browse on web | Ben | 1 | 1 | 0
| Give web same functionality as mobile | Ben | 1 | 1 | 0
| move back button to upper left corner (mobile) | Jordan | 0.1 | 0.1 | 0
| move back button to upper left corner (web) | Ben | 0.1 | 0.1 | 0
Deduct used ingredients from my pantry when a dish is prepared | Add cooked recipe button (web) meal plan and recipe detail? | Ben | 0.1 | 0.1 | 0
| Add cooked recipe button (mobile) | Jordan | 2 |  | 1
| Have pantry adjusted on backend when recipe is completed | Brianna | 2 | 2 | 0
| Implement call to backend to adjust pantry when cooked recipe is clicked (web) | Ben | 4 | 2 | 0
| Implement call to backend to adjust pantry when cooked recipe is clicked (mobile) | Jordan | 2 |  | 2
Add ingredients upon purchasing shopping list | Add purchased button (web) | Ben | 1 | 1 | 0
| Update wireframe for shopping list to support update quantity (web) | Ben | 0.5 | 0.25 | 0
| Add purchased button (mobile) | Jordan | 0.5 |  | 0.5
| Have pantry adjusted on backend when shopping is completed | Brianna | 2 | 2 | 0
| Implement call to backend to adjust pantry when shopping is complete (web) | Ben | 2 | 1 | 0
| Implement call to backend to adjust pantry when shopping is complete (mobile) | Jordan | 2 |  | 1
| Use case scenario for purchasing list | Jordan | 0.5 | 0.5 | 0
| Estimate Totals |  | 49.8 | 26.05 | 7.5